## Dashboard
Team Name | TomFoolery
User ID | Name
40238338 | Tung Lam Ha
40115222 | Gilbert Sedillo
40255597 | Ming-Hung Kao
40283099 | Jeff Zhong
40129282 | Navraj Jhajj

## Ming
User ID | Name
40255597 | Ming-Hung Kao
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-02-03 | 19:00 | N/A | 0.25 | Push frontend code to Github
2025-02-04 | 21:00 | #15 | 3 | Design the front end UI for the system | https://youtu.be/SqcY0GlETPk?si=KRnOMasw4xoiUfz3
2025-02-05 | 22:00 | #16 | 0.1 | Create a project on firebase
2/6/0225 | 19:00 | #6 | 1 | Merge code from Lam to the UI I built
2025-02-10 | 16:00 | N/A | 3 | Admin can create a text channel and add members
2025-02-12 | 20:00 | N/A | 1 | Member can only see the channels they belong to
2025-02-26 | 21:00 | #27 | 2 | Select Users in Direct Messaging Mode
2025-02-27 | 21:00 | #29 | 1 | Return Function
2025-03-06 | 22:00 | N/A | 1 | Update Readme file and Burndown chart
2025-03-07 | 19:00 | N/A | 0.5 | Upload sprint 2 deliverable to GitHub
2025-03-20 | 15:00 | #60 | 2 | Ensure unauthorized users can send message to another user
2025-03-20 | 19:00 | #59 | 0.5 | Use relative time for last seen timestamp
2025-03-20 | 19:00 | #58 | 2 | Green dot means online, red dot means offline
2025-03-20 | 19:00 | #57 | 0.5 | Both admin and member will have a list of registered users
2025-03-21 | 13:00 | N/A | 0.5 | Update Burndown chart
2025-03-21 | 15:00 | N/A | 0.5 | Update Meeting Minutes

## Lam
User ID | Name
40238338 | Tung Lam Ha
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-30 |  |  | 60 | Research on backend framework
2025-01-31 |  |  | 90 | Meeting #1
2025-01-31 |  |  | 15 | Creation of organization and github repository
2025-02-05 | 19:00 |  | 45 | Have team meeting #2 and taking meeting minutes
2025-02-06 | 23:00 | #9 & #10 | 240 | Dashboard UI side bar and message board
2025-02-07 | 13:00 | 7 & 9 | 45 | Merge Login UI and Dashboard UI
2025-02-10 | 17:00 | 2 & 3 | 90 | Tried new CSS framework
2025-02-19 | 22:00 | 2 & 3 & 8 | 120 | Built another prototype for design of log in and text channels
2025-02-28 | 21:00 | 2& 3 & 8 | 230 | testing with the last main with designed UI
2025-03-01 | 22:00 | 2& 3 & 9 | 45 | Debug testing
2025-03-12 | 21:00 | 17 & 8 | 180 | working on UI for dashboard
3 /19/2025 | 20:00 | 69 & 65 | 90 | Working on UI for message channel

## Gilbert
User ID | Name
40115222 | Gilbert Sedillo
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-29 | 17:00 | N/A | 0.75 | Research on front end technologies
2025-01-31 | 17:00 | N/A | 1.5 | Meeting #1
2025-02-05 | 19:00 | N/A | 0.75 | Team meeting #2
2025-02-06 | 19:00 | #12 | 4 | Distinguish user roles (Task 6) | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/issues/12
2025-02-12 | 18:00 | N/A | 2 | Clean up code and merge my branch to main | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/pull/20
2025-02-19 |  | N/A | 2 | Refactoring code, adding show channels functionality
2025-02-20 |  | #23 | 2 | Starting message sending | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/issues/23
2025-02-21 |  | #23, #24 | 3 | Channel message send/receive | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/issues/24
2025-03-05 |  | #48 | 1.5 | Pull request for new functionality | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/pull/48
2025-03-18 |  | #53 | 1 | Default channels
2025-03-19 |  | #53, #54 | 4 | Default channels/ private channels
2025-03-20 |  | #54, #55 | 2 | Private channels/leave+request channels

## Jeff
User ID | Name
40283099 | Jeff Zhong
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-30 | 17:00 | N/A | 0.25 | I made a discord for the entire group so we can communicate, I also asked the professor for extra information in regards of the project
2025-02-04 | 18:00 | #8 | 6 | First template of the website has been made. The login system and dashboard has been created with a tutorial | Link to the tutorial: https://www.youtube.com/watch?v=2hR-uWjBAgw
2025-02-05 | 20:00 | #6 | 3 | Made a functionning role system | Based on this tutorial: https://www.youtube.com/watch?v=0gLr-pBIPhI
2025-02-06 | 18:00 | N/A | 0.5 | Adjust GitHub details and make user stories more detailled
2025-02-06 | 19:00 | N/A | 0.5 | Make the tasks for the team to work on. Added despcriptions
2025-02-13 | 22:00 | N/A | 0.5 | Created all the github backlog for Sprint 2
2025-02-21 | 17:00 | #36 | 1 | Messed around with the current messaging system implemented by Tony and started to check the problems and work-arounds
2025-02-28 | 17:00 | #22 | 1 | Worked with the database and decide how to store messages, figure out algorithm of message storing
2025-03-03 | 18:00 | #22, #21 | 6 | Recombined everyone's code and made a full push to a new branch called REC-1. Combines the requirements for the Sprint 2
2025-03-06 | 20:00 | #34, #35, #36 | 1 | Checked the code with everyone. Test and make sure everyone can also do it on their computers for the Sprint
2025-03-14 | 20:00 | #68 | 1 | Tested Emoji's
2025-03-20 | 20:00 | #67, #61 | 7 | Made a small UI for chat, and made the quoting feature with a context menu

## Nav
User ID | Name
40129282 | Navraj Jhajj
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-02-01 | 18:00 | NA | 1.5h | (first time learning to code frontend)
2025-02-06 | 18:00 | #13 | 3h | Adapting to github, made this longer than it should.
2025-02-12 | 18:00 | #26 | 2h
2025-02-17 | 13:00 | #26 | 1.5h | worked on code to add delete feature
2025-02-18 | 13:30 | NA | 0.5h | Reread my code and make sure it was correct before committing
2025-02-20 | 20:45 | #26 | 0.5h | Tested my code, and making it more simple before pushing
2025-02-27 | 1:00 |  | 0.75h | Added delete channel button and function
2025-02-28 | 10:00 |  | 1h | Added delete chat button and function
2025-03-20 | 17:30 |  | 2h | Research on adding new function for user availability. + TESTING
2025-03-20 | 20:30 |  | 1h | Debug, and fix errors