## Dashboard
Team Name | TomFoolery
User ID | Name
40238338 | Tung Lam Ha
40115222 | Gilbert Sedillo
40255597 | Ming-Hung Kao
40283099 | Jeff Zhong
40129282 | Navraj Jhajj

## Ming
User ID | Name
40255597 | Ming-Hung Kao
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-02-03 | 19:00 | N/A | 0.25 | Push frontend code to Github
2025-02-04 | 21:00 | #15 | 3 | Design the front end UI for the system | https://youtu.be/SqcY0GlETPk?si=KRnOMasw4xoiUfz3
2025-02-05 | 22:00 | #16 | 0.1 | Create a project on firebase
2/6/0225 | 19:00 | #6 | 1 | Merge code from Lam to the UI I built
2025-02-10 | 16:00 | N/A | 3 | Admin can create a text channel and add members
2025-02-12 | 20:00 | N/A | 1 | Member can only see the channels they belong to
2025-02-26 | 21:00 | #27 | 2 | Select Users in Direct Messaging Mode
2025-02-27 | 21:00 | #29 | 1 | Return Function
2025-03-06 | 22:00 | N/A | 1 | Update Readme file and Burndown chart
2025-03-07 | 19:00 | N/A | 0.5 | Upload sprint 2 deliverable to GitHub

## Lam
User ID | Name
40238338 | Tung Lam Ha
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-30 |  |  | 60 | Research on backend framework
2025-01-31 |  |  | 90 | Meeting #1
2025-01-31 |  |  | 15 | Creation of organization and github repository
2025-02-05 | 19:00 |  | 45 | Have team meeting #2 and taking meeting minutes
2025-02-06 | 23:00 | #9 & #10 | 240 | Dashboard UI side bar and message board
2025-02-07 | 13:00 | 7 & 9 | 45 | Merge Login UI and Dashboard UI
2025-02-10 | 17:00 | 2 & 3 | 90 | Tried new CSS framework
2025-02-19 | 22:00 | 2 & 3 & 8 | 120 | Built another prototype for design of log in and text channels
2025-02-28 | 21:00 | 2& 3 & 8 | 230 | testing with the last main with designed UI
2025-03-01 | 22:00 | 2& 3 & 9 | 45 | Debug testing

## Gilbert
User ID | Name
40115222 | Gilbert Sedillo
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-29 | 17:00 | N/A | 0.75 | Research on front end technologies
2025-01-31 | 17:00 | N/A | 1.5 | Meeting #1
2025-02-05 | 19:00 | N/A | 0.75 | Team meeting #2
2025-02-06 | 19:00 | #12 | 4 | Distinguish user roles (Task 6) | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/issues/12
2025-02-12 | 18:00 | N/A | 2 | Clean up code and merge my branch to main | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/pull/20
2025-02-19 |  | N/A | 2 | Refactoring code, adding show channels functionality
2025-02-20 |  | #23 | 2 | Starting message sending | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/issues/23
2025-02-21 |  | #23, #24 | 3 | Channel message send/receive | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/issues/24
2025-03-05 |  | #48 | 1.5 | Pull request for new functionality | https://github.com/Tomfoolery-concordia-soen341/Tomfoolery-SOEN341_Project_W25/pull/48

## Jeff
User ID | Name
40283099 | Jeff Zhong
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-01-30 | 17:00 | N/A | 0.25 | I made a discord for the entire group so we can communicate, I also asked the professor for extra information in regards of the project
2025-02-04 | 18:00 | #8 | 6 | First template of the website has been made. The login system and dashboard has been created with a tutorial | Link to the tutorial: https://www.youtube.com/watch?v=2hR-uWjBAgw
2025-02-05 | 20:00 | #6 | 3 | Made a functionning role system | Based on this tutorial: https://www.youtube.com/watch?v=0gLr-pBIPhI
2025-02-06 | 18:00 | N/A | 0.5 | Adjust GitHub details and make user stories more detailled
2025-02-06 | 19:00 | N/A | 0.5 | Make the tasks for the team to work on. Added despcriptions
2025-02-13 | 22:00 | N/A | 0.5 | Created all the github backlog for Sprint 2
2025-02-21 | 17:00 | #36 | 1 | Messed around with the current messaging system implemented by Tony and started to check the problems and work-arounds
2025-02-28 | 17:00 | #22 | 1 | Worked with the database and decide how to store messages, figure out algorithm of message storing
2025-03-03 | 18:00 | #22, #21 | 6 | Recombined everyone's code and made a full push to a new branch called REC-1. Combines the requirements for the Sprint 2
2025-03-06 | 20:00 | #34, #35, #36 | 1 | Checked the code with everyone. Test and make sure everyone can also do it on their computers for the Sprint
write two test cases and make the CI on github Actions
Due by sunday 8 PM
make sure that they both succeed
Send an E-mail | 1. For tbe entire YML files and github actions make the test cases for CI/CD
2. Meeting minutes of Friday march 7th and make everything as a usual meeting minutes, send to the professor
Last Step: | Upload burndown chart, sprint meetings, to the github

## Nav
User ID | Name
40129282 | Navraj Jhajj
Date | Time Started | Issue worked on | Time spent (hours) | Comments/Notes | Links
2025-02-01 | 18:00 | NA | 1.5h | (first time learning to code frontend)
2025-02-06 | 18:00 | #13 | 3h | Adapting to github, made this longer than it should.
2025-02-12 | 18:00 | #26 | 2h
2025-02-17 | 13:00 | #26 | 1.5h | worked on code to add delete feature
2025-02-18 | 13:30 | NA | 0.5h | Reread my code and make sure it was correct before committing
2025-02-20 | 20:45 | #26 | 0.5h | Tested my code, and making it more simple before pushing
2025-02-27 | 1:00 |  | 0.75h | Added delete channel button and function
2025-02-28 | 10:00 |  | 1h | Added delete chat button and function