## Sprint 1
Issue # | User Story Title/Task Title | Story Points | Due Date | Description/Associated Tasks | Difficulty Level (0,1,2,3,4,5) | Priority | Risk | Assign | Sprint
6 | US-1 - Build User Authentication | 4 | 2025-02-07 | As a user, I want to be able to login to the system so that I can access the dashboard. | 3 | 1 | Low | Jeff, Ming, Gilbert, Nav | 2
12 | Task 6 - Distinguish a user and an Admin | 2 | 2025-02-07 | When you are authenticated, make the system recognize the Admin vs the user. | 4 | 1 | Low | Gilbert | 2
13 | Task 5 - Error handling | 1 | 2025-02-07 | Make a proper error statement if the username does not exist. | 2 | 3 | Low | Nav | 2
14 | Task 4 - Registering a new user | 1 | 2025-02-07 | Make a button to register a user in case the user does not exist. When the user registers, the user can enter their email and password. The information should store into a database where their account will be saved. | 2 | 4 | High | Jeff, Ming | 2
7 | US-2 - Build Frontend with React | 1 | 2025-02-07 | As a user, I want to be able to interact with the system so that I can navigate and understand the system better. Related to #15 | 2 | 3 | Medium | Lam, Ming | 2
15 | Task 7 - Make Login interface | 1 | 2025-02-07 | Make the graphical interface user-friendly. Must be able to distinguish each element (login vs. register) and distinguish the various fields (email vs password) | 1 | 2 | Medium | Ming | 2
8 | US-3 - Build Dashboard | 3 | 2025-02-07 | As a User, after signing in the system, I want to be able to access the dashboard and see my name | 2 | 2 | Medium | Lam | 2
8 | Task 1 - Missing graphic interface | 1 | 2025-02-07 | Make a proper graphic interface for the dashboard. It needs to be easy to follow and navigate. | 1 | 3 | Medium | Lam | 2
10 | Task 2 - Missing Role specification on Dashboard | 1 | 2025-02-07 | The dashboard displays the role of the user when they log-in. The role options that are displayed are users and admins. The role is displayed right under the user's name. | 2 | 1 | Low | Jeff, Gilbert | 2
19 | Task 9 - Display user's login information | 1 | 2025-02-07 | When the user logs into the system, they can see their email displayed. | 2 | 2 | Low | Jeff | 2

## Sprint 2
Issue # | User Story Title/Task Title | Story point | Description/Associated Tasks | Difficulty Level (0,1,2,3,4,5) | Priority | Risk | Assign | Sprint
21 | US 4 - Text Channels | 10 | Text channels should accessible to users and admin. Messages are visible for both of them. Only admin can moderate/delete messages. | 3 | 2 | No | Jeff, Ming | 2
10 | Task 10 - Message Sending | 3 | Messages should be sent to text channels and visible by other users | 3 | 3 | No | Gilbert | 2
11 | Task 11 - Message retrieving | 2 | Messages shall appear once users enter text channels | 3 | 2 | No | Gilbert | 2
17 | Task 17 - General Information | 1 | Sender's name and timestamp shall appears in the channels | 1 | 1 | No | Nav | 2
12 | Task 12 - Admin permission | 4 | Admin must be able to delete messages and remove members from the channel | 4 | 1 | No | Nav | 2
22 | US 5 - Direct Messaging | 9 | Users can have private chat with another user. Messages are visible all the time. | 3 | 2 | No | Jeff, Ming | 2
13 | Task 13 - Select users in Direct Messaging Mode | 3 | Users can have private chat with another user. Messages are visible all the time. | 3 | 2 | No | Ming | 2
14 | Task 14 - Privacy | 2 | Only users in the chats can see the messages | 2 | 1 | No | Jeff | 2
15 | Task 15 - Return Function | 1 | When users are in the chat, they shall return to the list of user by clicking return button | 1 | 1 | No | Ming | 2
16 | Task 16 - In real-time message | 3 | Messages shall be displayed no more than 5 seconds after the messages are sent. | 3 | 1 | No | Jeff | 2